## Product Backlog
Task | Value | Effort | MVP | Sprint | Done
Update presentation for clarity | $$$ | 5 | Yes | 1 | 2025-09-12
Cleanup directory and Git Repository | $$ | 13 | Yes | 1 | 2025-09-12
Updated README for MVP | $ | 2 | Yes | 1 | 2025-09-12
Convert Scraping and Analysis Scripts from Jupyter to .py | $$ | 5 | No | 2
Refactor Scraping script to use zip files and extraction | $$ | 13 | No | 2 | 2025-09-17
Refactor analysis scripts to include station ID in data | $$ | 8 | No | 2
Create Unit Testing for Scraping and Analysis Scripts | $$$ | 13 | No
Create Candidate Analysis Script with daily analysis and weighting function | $$$$ | 21 | No
Update presentation with full Candidate analysis | $$$$ | 8 | No
Refactor Plot Jupyter Notebook to be presentable | $$$ | 8 | No
Full Documentation overhaul of scripts | $$ | 21 | No
Automate Backlog Spreadsheet with Sprint Tabs | $$ | 8 | No
Update thunder data analysis to use a centered moving 10 year average | $$$ | 21 | No